Prof.Tirup Parmar
Unit I
In this introduction the main questions to be addressed will be:
What is software project management? Is it really different from ‘ordinary’
project management?
How do you know when a project has been successful? For example, do the
expectations of the customer/client match those of the developers?
The two key questions are:
1.
What exactly is software project management?
This is going to be tackled by looking firstly at what is meant by ‘project’. We are then going to
examine whether ‘software project management’ is really different from ‘normal’ project
management. Is there anything special about software as opposed to other engineered artefacts?
2.
How do we define whether a project is a success or not?
The point about studying project management is to be able to have successful projects. So how do we
know if we have been successful?
Why is project management important?
Large amounts of money are spent on ICT e.g. UK government in 2003-4 spent £2.3
billions on contracts for ICT and only £1.4 billions on road building
Project often fail – Standish Group claim only a third of ICT projects are successful. 82%
were late and 43% exceeded their budget.
Poor project management a major factor in these failures
The methodology used by the Standish Group to arrive at their findings has been criticized, but the
general perception of the prevalence of ICT project failure is still clear.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 4
https://E-next.in

---
What is a project?
Some dictionary definitions:
“A specific plan or design”
“A planned undertaking”
“A large undertaking e.g. a public works scheme”
Longmans dictionary
Key points above are planning and size of task
An endeavor with specific objectives:
Usually consists of multiple tasks
With defined precedence relationships
With a specific time period for completion
Non-Software Examples:
A wedding
An MBA degree
A house construction project
A political election campaign
Here are some definitions of ‘project’. No doubt there are other ones: for example
‘Unique process, consisting of a set of coordinated and controlled activities with start and finish dates,
undertaken to achieve an objective conforming to specific requirements, including constraints of time,
cost and resources’
BSO ISO 10006: 1997
What is a Task?
A small piece of work:
Meant to accomplish a straightforward goal
Effort of no longer than a few person-hours
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 5

---
Involves only a few people
May or may not be a part of some project
Usually repetition of a previously accomplished task
Process management may be relevant!
Non-software Examples:
Attend a lecture class
Buy a chocolate from the market
Book a railway ticket
Jobs versus projects
‘Jobs’ – repetition of very well-defined and well understood tasks with very little uncertainty
‘Exploration’ – e.g. finding a cure for cancer: the outcome is very uncertain
Projects – in the middle!
On the one hand there are repetitive jobs a similar task is carried out repeatedly, for example Kwikfit
replacing a tyre on a car or a lecturer giving an introductory talk on project management. The task is
well-defined and there is very little uncertainty. In some organizations, software development might
tend to be like this – in these environments software process management might be more important
than software project management
On the other hand some exploratory activities are very uncertain. Some research projects can be like
this – we may not be sure what the outcome will be, but we hope that we will learn some things of
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 6

---
importance. It may be very difficult to come up with precise plans, although we would probably have
some idea of a general approach.
Projects seem to come somewhere between these two extremes. There are usually well-defined
hoped-for outcomes but there are risks and uncertainties about achieving those outcomes.
Characteristics of projects
A task is more ‘project-like’ if it is:
Non-routine
Planned
Aiming at a specific target
Carried out for a customer
Carried out by a temporary work group
Involving several specialisms
Made up of several different phases
Constrained by time and resources
Large and/or complex
Exercise 1.1 in the Software Project Management text is a good way of introducing this material if you
have time. I have found this exercise to be a good ‘ice-breaker’. Get each student to list the example
activities in an order which matches the degree to which they merit the description of ‘project’. You
st
nd
rd
can create a grid on a whiteboard with the projects on the vertical axis and the positions 1
, 2
, 3
 etc
on the horizontal axis. You then go through asking how many put ‘producing a newspaper’ first,
second, etc. (Avoid making jokes about this being like the Eurovision song contest). This is time-
consuming but it does mean that every student participates in building up a general picture of
people’s perceptions, and you can discuss disagreements in perceptions as you go along.
Are software projects really different from other projects?
Not really …but... The factors
Invisibility
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 7

---
Complexity
Conformity
Flexibility
make software more problematic to build than other engineered artefacts.
This is based on Fred Brooks’ paper No Silver Bullet: Essence and Accidents of Software Engineering
which appeared in IEEE Computer 20(4) pp10-19 April 1987
Contract management versus technical project management
Projects can be:
In-house: clients and developers are employed by the same organization
Out-sourced: clients and developers employed by different organizations
‘Project manager’ could be:
 a ‘contract manager’ in the client organization
 a technical project manager in the supplier/services organization
In general the book looks at things from the point of view of the technical software project manager.
Activities covered by project management
Feasibility study:
Is project technically feasible and
worthwhile from a business point
of view?
Planning:
Only done if project is feasible
Execution:
Implement plan, but plan may be
changed as we go along
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 8

---
There are two key points here.
1.
Often you see something like ‘feasibility study’ being put as the first stage of development life
cycle, and indeed it might be. However, the recommendation of the feasibility study might be
not to carry out the proposed project. Planning of the project should therefore take place after
the feasibility study (or as a part of the feasibility study perhaps). Clearly the feasibility study
itself might need a plan.
2.
All plans are to some extent provisional and subject to change. The key point is that the
evolving plan allows us to control the project.
The software development life-cycle (ISO 12207)
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 9

---
Note that this is a technical model. It identifies the technical constraints on the order activities are
done. This does NOT imply that a ‘waterfall’ approach is the only way to organize projects. The
technical model could be implemented as increments or in an evolutionary manner.
ISO 12207 life-cycle
Requirements analysis
Requirements elicitation: what does the client need?
Analysis: converting ‘customer-facing’ requirements into equivalents that
developers can understand
Requirements will cover
•
Functions
•
Quality
•
Resource constraints i.e. costs
The key point here is that requirement analysis has to face in (at least) two different directions. It
needs to communicate and elicit the requirements of the users, speaking in their language. It needs to
organize and translate those requirements into a form that developers can understand and relate to.
Architecture design
Based on system requirements
Defines components of system: hardware, software, organizational
Software requirements will come out of this
Code and test
Of individual components
Integration
Putting the components together
The software project will almost certainly be part of a larger project which has non-software
elements. In a software engineering environment it could be the software will be embedded in
hardware product of some kind. Thus there are system requirements for the product as a
whole and software requirements for the software element.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 10

---
In a business information systems environment, the software development could be a
relatively minor part of a much larger organizational change project.
Qualification testing
Testing the system (not just the software)
Installation
The process of making the system operational
Includes setting up standing data, setting system parameters, installing on
operational hardware platforms, user training etc
Acceptance support
Including maintenance and enhancement
The confusion about what ‘aimplementation’ really means could be mentioned. Does it mean
implementing the design (that is, coding) or implementing the complete system in its user
environment? It is best to use ‘installation’ to describe the latter in order to avoid confusion.
Plans, methods and methodologies
A plan of an activity must be based on some idea of a method of work. While a method relates to a
type of activity in general, a plan takes one or more methods and converts them into real activities by
identifying:
•
Start and end dates
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 11

---
•
Who will carry it out
•
What tools and materials would be needed.
A methodology is a set of related methods. Strictly speaking ‘methodology’ ought to mean the study
of methods!
Some ways of categorizing projects
Distinguishing different types of project is important as different types of task need different
project approaches e.g.
Voluntary systems (such as computer games) versus compulsory systems e.g. the order
processing system in an organization
Information systems versus embedded systems
Objective-based versus product-based
Product-development versus outsourced
With objective-based projects, a general objective or problem is defined, and there are several

different ways in which that objective could be reached. The project team have freedom to
select what appears to be the most appropriate approach.
With product-based projects, the product is already very strictly defined and the development

team’s job is to implement the specification with which they have been presented.
Arguably, information systems projects are more likely to be objective-based than is the case

with software engineering.
In many cases, an objective-based project could consider a problem and recommend a

solution that is then implemented by a product-based project.
Exercise 1.5 in the text is relevant here.

Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 12

---
Fig. A Categorization of Software Projects
Two Types of Software Projects
Software product development projects
Software services projects
Software Services
Software service is an umbrella term, includes:
Software customization
Software maintenance
Software testing
Also contract programmers who carry out coding or any other assigned
activities.
Stakeholders
These are people who have a stake or interest in the project
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 13

---
In general, they could be users/clients or developers/implementers
They could be:
Within the project team
Outside the project team, but within the same organization
Outside both the project team and the organization
Different stakeholders may have different objectives – need to define common project
objectives
Each stakeholder will have their own goals and concerns in relation to the project which may be
different from those of the project as a whole. For example, a software developer might work to make
a living, pay the mortgage, learn new things, solve interesting problems. The main stakeholders need,
however, to understand and accept overall project objectives that everyone can agree to.
See Exercise 1.6 in the text.
Setting objectives
Answering the question ‘What do we have to do to have a success?’
Need for a project authority
Sets the project scope
Allocates/approves costs
Could be one person - or a group
Project Board
Project Management Board
Steering committee
Different people who are involved in a project (Stakeholders) will have different interests in

the project and are likely to see different outcomes as being important.
For example, end-users would want a system that is ‘user-friendly’, that is, easy to learn and

to use, and a system that helps rather than hinders them from doing their jobs. Their
managers may be more interested in whether the new system would allow them to reduce
staffing levels.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 14

---
It is important therefore that a set of clearly defined objectives are identified and published for

the project. Some individual or group needs to be pinpointed who acts as the main client for
the project.

See Exercise 1.7 in the text.
Objectives
Informally, the objective of a project can be defined by completing the statement:
The project will be regarded as a success
if……….
…………
Rather like post-conditions for the project
Focus on what will be put in place, rather than how activities will be carried out
The focus here needs to be on what the situation will be when the project is completed. In what ways
will the world be different? The objectives should avoid describing activities:
th
e.g. ‘a new payroll application will be operational by 4
 April’ not ‘design and code a new payroll
application’
Objectives should be SMART
S – specific, that is, concrete and well-defined
M – measurable, that is, satisfaction of the objective can be objectively judged
A – achievable, that is, it is within the power of the individual or group concerned to meet the
target
R – relevant, the objective must relevant to the true purpose of the project
T – time constrained: there is defined point in time by which the objective should be achieved
I have seen some places where the R is said to stand for ‘resource-constrained’, that is that there is a
target cost associated with the achievement of the objective.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 15

---
Goals/sub-objectives
These are steps along the way to achieving the objective
Informally, these can be defined by completing the sentence
To reach objective X, the following must be in place
A……………
B……………
C…………… etc
Scoring a goal in football is a ‘goal’ or sub-objective on the way to achieving the overall objective of
winning the match. Sub-objectives and objectives can be nested in a hierarchy, so that the objective of
winning the match could itself be a goal or sub-objective on the way to winning the league etc.
Often a goal can be allocated to an individual
Individual might have the capability of achieving goal on their own, but not the overall objective
e.g.
Overall objective – user satisfaction with software product
Analyst goal – accurate requirements
Developer goal – reliable software
Goals can be formulated in such a way that they represent what an individual or group need to do to
contribute to the success of the project’s objectives.
In the example above, the analyst or developer, by themselves, cannot guarantee user satisfaction.
However, the analyst can contribute to the achievement of the objective by making sure the users’
requirements are accurately recorded and the developer by making sure that the software is reliable.
See Exercise 1.7 in the text.
Measures of effectiveness
How do we know that the goal or objective has been achieved?
By a practical test, that can be objectively assessed.
e.g. for user satisfaction with software product:
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 16

---
Repeat business – they buy further products from us
Number of complaints – if low etc etc
See Exercise 1.8 in the text.
The business case
Benefits of delivered project must outweigh costs
Costs include:
-
Development
-
Operation
Benefits
Quantifiable
Non-quantifiable
It is not always possible to put a precise financial on the benefits of a project. The client’s willingness
to pay up to a certain price to get a project implemented implies that they have informally identified a
value to them of getting that project implemented.
Project success/failure
Degree to which objectives are met
this
In general if, for example, project is running out of time,
can be recovered for by reducing scope or increasing
costs. Similarly costs and scope can be protected by
adjusting other corners of the ‘project triangle’.
Other success criteria
These can relate to longer term, less directly tangible assets
Improved skill and knowledge
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 17

---
Creation of assets that can be used on future projects e.g. software libraries
Improved customer relationships that lead to repeat business
What is management?
This involves the following activities:
Planning – deciding what is to be done
Organizing – making arrangements
Staffing – selecting the right people for the job
Directing – giving instructions
Monitoring – checking on progress
Controlling – taking action to remedy hold-ups
Innovating – coming up with solutions when problems emerge
Representing – liaising with clients, users, developers and other stakeholders
Exercise 1.6 (a day in the life of a project manager) is of relevance here.
Project Planning
Carried out before development starts.
Important activities:
Estimation
Scheduling
Staffing
Risk management
Miscellaneous plans
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 18

---
In the project initiation stage, an initial plan is made. As the project start, the project is monitored and
controlled to proceed as per the plan. But, the initial plan is refined from time to time to factor in
additional details and constraints about the project become available.
Traditional versus Modern Project Management
Projects are increasingly being based on either tailoring some existing product or
reusing certain pre-built libraries.
Facilitating and accommodating client feedbacks
Facilitating customer participation in project development work
Incremental delivery of the product with evolving functionalities.
Rather than making a long term project completion plan, the project manager now plans all
incremental deliveries with evolving functionalities. This type of project management is often called
Extreme project management.
Management control
Data – the raw details
e.g. ‘6,000 documents processed at
location X’
Information – the data is processed to
produce something that is meaningful and
useful
e.g. ‘productivity is 100 documents a day’
Comparison with objectives/goals
e.g. we will not meet target of processing
st
all documents by 31
 March
Modelling – working out the probable
outcomes of various decisions
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 19

---
e.g. if we employ two more staff at location X how quickly can we get the documents
processed?
Implementation – carrying out the remedial actions that have been decided upon
The authors’ view is that an initially defective plan can often be remedied by good project control and
management.
Project Management Processes
In the project initiation stage, an initial plan is made. As the project starts, the project is
executed and controlled to proceed as planned. Finally, the project is closed.
Project Management Life Cycle Versus Product Development Life Cycle
During the software development life cycle, the software developers carry out several types of
development processes. On the other hand, during the software project management life cycle,
the software project manager carries out several project management processes
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 20

---
Phases of Project Management Life Cycle
Project Initiation
During the project initiation phase it is crucial for the champions of the project to
develop a thorough understanding of the important characteristics of the project.
In his W5HH principle, Barry Boehm summarized the questions that need to be asked
and answered in order to have an understanding of these project characteris tics.
W5HH Principle
A series of questions that lead to a definition of key project characteristics:
Why is the software being built?
What will be done?
When will it be done?
Who is responsible for a function?
Where are they organizationally located?
How will the job be done technically and managerially?
How much of each resource is needed?
Project Planning
Various plans are made:
Project plan: Assign project resources and time frames to the tasks.
Resource plan: List the resources, manpower and equipment that required to
execute the project.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 21

---
Financial plan: plan for manpower, equipment and other costs.
Quality plan: Plan of quality targets and control.
Risk plan: Identification of the potential risks, their prioritization and a plan for
the actions that would be taken to contain the different risks.
Project Execution
Tasks are executed as per the project plan
Monitoring and control processes are executed to ensure that the tasks are executed as
per plan
Corrective actions are initiated whenever any deviations from the plan are noticed.
Project Closure
Involves completing the release of all the required deliverables to the customer along
with the
necessary documentation.
Subsequently, all the project resources are released and supply agreements with the
vendors are terminated and all the pending payments are completed.
Finally, a post-implementation review is undertaken to analyze the project performance
and to list the lessons learnt for use in future projects.
Key points in lecture
Projects are non-routine - thus uncertain
The particular problems of projects e.g. lack of visibility
Clear objectives which can be objectively assessed are essential
Stuff happens. Not usually possible to keep precisely plan – need for control
Communicate, communicate, communicate!
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 22

---
Main topics to be covered
The business case for a project
Project portfolios
Project evaluation
Cost benefit analysis
Cash flow forecasting
Programme management
Benefits management
The business case
Feasibility studies can also act as a ‘business case’
Provides a justification for starting the project
Should show that the benefits of the project will exceed development, implementation
and operational costs
Needs to take account of business risks
See page 22
It is worth recalling the difference between project success (the project is successfully completed) and
business risks (the new product or system successfully established by the project goes on to generate
benefits for the organization).
Contents of a business case
1.
Introduction/ background
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 23

---
2.
The proposed project
3.
The market
4.
Organizational and operational infrastructure
5.
The benefits
6.
Outline implementation plan
7.
Costs
8.
The financial case
9.
Risks
10.
Management plan
Introduction/background: describes a problem to be solved or an opportunity to be
exploited
The proposed project: a brief outline of the project scope
The market: the project could be to develop a new product (e.g. a new computer
game). The likely demand for the product would need to be assessed.
Organizational and operational infrastructure: How the organization would need to
change. This would be important where a new information system application was
being introduced.
Benefits These should be express in financial terms where possible. In the end it is up
to the client to assess these – as they are going to pay for the project.
Outline implementation plan: how the project is going to be implemented. This
should consider the disruption to an organization that a project might cause.
Costs: the implementation plan will supply information to establish these
Financial analysis: combines costs and benefit data to establish value of project
Financial analysis – we will see later that the comparative value of costs and benefits may not be
obvious as the timing of costs and benefits need to be taken into consideration.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 24

---
Project portfolio management
The concerns of project portfolio management include:
Evaluating proposals for projects
Assessing the risk involved with projects
Deciding how to share resources between projects
Taking account of dependencies between projects
Removing duplication between projects
Checking for gaps
There are three elements to PPM:
1.
Project portfolio definition
Create a central record of all projects within an organization
Must decide whether to have ALL projects in the repository or, say, only ICT
projects
Note difference between new product development (NPD) projects and renewal
projects e.g. for process improvement
2.
Project portfolio management
Actual costing and performance of projects can be recorded and assessed
3.
Project portfolio optimization
Information gathered above can be used achieve better balance of projects e.g. some
that are risky but potentially very valuable balanced by less risky but less valuable projects
You may want to allow some work to be done outside the portfolio e.g. quick fixes
Cost benefit analysis (CBA)
This relates to an individual project. You need to:
Identify all the costs which could be:
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 25

---
Development costs
Set-up
Operational costs
Identify the value of benefits
Check benefits are greater than costs
Section 2.4 of the text expands this material.
Exercise 2.1 requires students to identify the potential costs and benefits of the Brightmouth College
payroll application.
Product/system life cycle cash flows
The timing of costs and income for a product of system needs to be estimated.
The development of the project will incur costs.
 When the system or product is released it will generate income that gradually pays off
costs
Some costs may relate to decommissioning – think of demolishing a nuclear power
station.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 26

---
Net profit
Year
Cash-flow
0
-100,000
1
10,000
2
10,000
3
10,000
4
20,000
5
100,000
Net profit
50,000
 ‘Year 0’ represents all the costs before system is operation
‘Cash-flow’ is value of income less outgoing
Net profit value of all the cash-flows for the lifetime of the application
See Section 2.5 for further details. Exercise 2.3 is applicable here
Pay back period
This is the time it takes to start generating a surplus of income over outgoings. What would it
be below?
Year
Cash-flow
Accumulated
0
-100,000
-100,000
1
10,000
-90,000
2
10,000
-80,000
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 27

---
3
10,000
-70,000
4
20,000
-50,000
5
100,000
50,000
The payback period would be about 4.5 years. This can be calculated as the last year in which the
accumulated cash flow was negative + (absolute accumulated cash flow at the end of that year / cash-
flow for the next year) e.g. year 4 + (50,000/100,000). This assumes that the flow of cash is constant
throughout the year in question e.g. £100,000/12 or £8,333 a month in year 5
Exercise 2.3. in the text is relevant here.
Return on investment (ROI)
Exercise 2.4. gives further practice is calculating ROI.
Net present value
Would you rather I gave you £100 today or in 12 months time?
If I gave you £100 now you could put it in savings account and get interest on it.
If the interest rate was 10% how much would I have to invest now to get £100 in a year’s time?
This figure is the net present value of £100 in one year’s time
If you invested £91 now you would get £9.10 in interest which would give you £100.10 in 12 months.
The interest rate of 10% is used purely to make it easy to do the calculations, not because it is a
realistic rate.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 28

---
Discount factor
t
Discount factor = 1/(1+r)
r is the interest rate (e.g. 10% is 0.10)
t is the number of years
In the case of 10% rate and one year
Discount factor = 1/(1+0.10) = 0.9091
In the case of 10% rate and two years
Discount factor = 1/(1.10 x 1.10) =0.8294
Applying discount factors
Discounted cash
Year
Cash-flow
Discount factor
flow
0
-100,000
1.0000
-100,000
1
10,000
0.9091
9,091
2
10,000
0.8264
8,264
3
10,000
0.7513
7,513
4
20,000
0.6830
13,660
5
100,000
0.6209
62,090
NPV
618
NPV is the sum of the discounted cash flows for all the years of the ‘project’ (note that in NPV terms
the lifetime of the completed application is included in the ‘project’)
The figure of £618 means that £618 more would be made than if the money were simply invested at
10%. An NPV of £0 would be the same amount of profit as would be generated by investing at 10%.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 29

---
Internal rate of return
Internal rate of return (IRR) is the discount rate that would produce an NPV of 0 for the
project
Can be used to compare different investment opportunities
There is a Microsoft Excel function which can be used to calculate
The Excel function in question is =IRR.
Dealing with uncertainty: Risk evaluation
project A might appear to give a better return than B but could be riskier
Draw up a project risk matrix for each project to assess risks – see next overhead
For riskier projects could use higher discount rates
Example of a project risk matrix
In the table ‘Importance’ relates to the cost of the damage if the risk were to materialize and
‘likelihood’ to the probability that the risk will actual occur. ‘H’ indicates ‘High’, ‘M’ indicates ‘medium’
and ‘L’ indicates ‘low’. The issues of risk analysis are explored in much more depth in chapter 7.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 30

---
Decision trees
The diagram here is figure 2.2 in the text.
This illustrates a scenario that could relate to the IOE case study. Say Amanda is responsible
for extending the invoicing system. An alternative would be to replace the whole of the
system. The decision is influenced by the likelihood of IOE expanding their market. There is a
strong rumour that they could benefit from their main competitor going out of business: in
this case they could pick up a huge amount of new business, but the invoicing system could
not cope. However replacing the system immediately would mean other important projects
would have to be delayed.
The NPV of extending the invoicing system is assessed as £75,000 if there is no sudden
expansion. If there were a sudden expansion then there would be a loss of £100,000. If the
whole system were replaced and there was a large expansion there would be a NPV of
£250,000 due to the benefits of being able to handle increased sales. If sales did not increase
then the NPV would be -£50,000.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 31

---
The decision tree shows these possible outcomes and also shows the estimated probability of
each outcome.
The value of each outcome is the NPV multiplied by the probability of its occurring. The value
of a path that springs from a particular decision is the sum of the values of the possible
outcomes from that decision. If it is decided to extend the system the sum of the values of the
outcomes is £40,000 (75,000 x 0.8 – 100,000 x 0.2) while for replacement it would be £10,000
(250,000 x 0.2 – 50,000 x 0.80). Extending the system therefore seems to be the best bet (but
it is still a bet!).
Programme management
One definition:
‘a group of projects that are managed in a co-ordinated way to gain benefits that would
not be possible were the projects to be managed independently’ Ferns
The quotation is from a paper that appeared in the International Journal of Project Management
August 1991
Programmes may be
Strategic
Business cycle programmes
Infrastructure programmes
Research and development programmes
Innovative partnerships
See Section 2.7

Strategic

Several projects together implement a single strategy. For example, merging two

organizations will involve many different activities e.g. physical re-organization of
offices, redesigning the corporate image, merging ICT systems etc. Each of these
activities could be project within an overarching programme.
Business cycle programmes

Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 32

---
A portfolio of project that are to take place within a certain time frame e.g. the next

financial year
Infrastructure programmes

In an organization there may be many different ICT-based applications which share

the same hardware/software infrastructure
Research and development programmes

In a very innovative environment where new products are being developed, a range

of products could be developed some of which are very speculative and high-risk but
potentially very profitable and some will have a lower risk but will return a lower
profit. Getting the right balance would be key to the organization’s long term success
Innovative partnerships

e.g. pre-competitive co-operation to develop new technologies that could be

exploited by a whole range of companies
Programme managers versus project managers
Programme manager
Project manager
Many simultaneous projects
One project at a time
Personal relationship with
Impersonal relationship with
skilled resources
resources
Minimization of demand for
Optimization of resource use
resources
Projects tend to be seen as
Projects tend to be seen as
similar
unique
The programme manager may well have a pool of staff upon which to call. He/she will be concerned
with ensuring the best use of staff e.g ensuring that staff have regular work with no periods of
enforced idleness between project tasks. The project leader would think in terms of ‘I need a Java
programmer for four weeks’ without being concerned which specific person it is (beyond obvious
concerns that they are fully capable).
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 33

---
Strategic programmes
Based on OGC approach
Initial planning document is the Programme Mandate describing
The new services/capabilities that the programme should deliver
How an organization will be improved
Fit with existing organizatioal goals
A programme director appointed a champion for the scheme
The material here is based on the UK government’s Office of Government Commerce (OGC)

approach which is described in detail in their publication Managing successful programmes.
The programme director should be someone who is in a prominent position in the organization

so that the seriousness and commitment of the organization to the programme are made
clear.
An example of what might be a programme is given in Section 2.9 in the text. It might be

found at the IOE company that the customers’ experience of the organization can be very
variable and inconsistent. The employee who records the customer’s requirements is different
from the people who actually carry out the work and different again from the clerk who deals
with accounts. Different maintenance engineers deal with different types of equipment. A
business objective might be to present a consistent and uniform interface to the client. This
objective might need changes to a number of different systems which until now have been
largely self-contained. The work to reorganize each individual area might be treated as
separate projects, co-ordinated at a higher level as a programme.
Next stages/documents
The programme brief – equivalent of a feasibility study: emphasis on costs and benefits
The vision statement – explains the new capability that the organization will have
The blueprint – explains the changes to be made to obtain the new capability
The programme brief – is it worth it?

The vision statement – the ‘what’

The blueprint – the ‘how’

Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 34

---
Benefits management
•
 Providing an organization
with a capability does not
guarantee that this will provide
benefits envisaged – need for
benefits management
•
This has to be outside the
project – project will have been
completed
•
Therefore done at programme level
To carry this out, you must:
Define expected benefits
Analyse balance between costs and benefits
Plan how benefits will be achieved
Allocate responsibilities for their achievement
Monitor achievement of benefits
Benefit profiles can be produced that document when and how it is planned that the benefits

will be experienced.
As different components of the new capability are developed, a series of tranches of projects

(projects grouped in different steps of the programme) may be completed, each with a set of
associated benefits.
The achievement of benefits might be made the responsibility of staff who are designated as

business change managers.
Benefits
These might include:
Mandatory requirement
Improved quality of service
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 35

---
Increased productivity
More motivated workforce
Internal management benefits
You could argue that as you have to comply with a mandatory requirement, the question of

benefits is irrelevant in this case. However as failure to comply will a negative outcome (e.g.
not being able to trade), avoiding that negative outcome is clearly a benefit which could be
costed.
‘Internal management benefits’ includes things like better decision-making. In the case of an

insurance company a deeper analysis of insurance claims might help identify types of business
that are most risky and allow the company to adjust premiums to cover these.
Risk reduction
Economies
Revenue enhancement/acceleration
Strategic fit
‘Economies’ refers to cost-cutting e.g. using an automated telephone system to direct calls

without human intervention could allow an organization to reduce staff.
Revenue enhancement/acceleration e.g. the sooner that bills reach the customers, the sooner

they can pay them.
‘Strategic fit’ A change might not benefit any single group within an organization but might

have to be made to obtain a benefit for the organization as a whole.
Quantifying benefits
Benefits can be:
Quantified and valued e.g. a reduction of x staff saving £y
Quantified but not valued e.g. a decrease in customer complaints by x%
Identified but not easily quantified – e.g. public approval for a organization in the
locality where it is based
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 36

---
Remember!
A project may fail not through poor management but because it should never have been
started
A project may make a profit, but it may be possible to do something else that makes
even more profit
A real problem is that it is often not possible to express benefits in accurate financial
terms
Projects with the highest potential returns are often the most risky
‘Step Wise’ – aspirations
Practicality
tries to answer the question ‘what do I do now?’
Scalability
useful for small project as well as large
Range of application
Accepted techniques
e.g. borrowed from PRINCE etc
The motivation for identifying an overall framework was that students, and others, were often at a
loss as to where to start when new to project planning. A structured approach was seen as catering
for the needs of such people.
Students are perhaps most likely to come into contact with some kind of project planning (i) when they
are involved in student projects, especially those carried in groups and (ii) if they are members of a
project team when they are undertaking a placement year in industry. The first situation is probably
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 37

---
quite small-scale compared to the second. The same general principles of planning however relate to
both.
The approach described here is designed to be applicable to a range of different types of project. For
example, multimedia projects are not explicitly discussed, but one of the authors teaches a course
project management for multimedia and the general approach described here seems to work
satisfactorily when applied to these type of projects.
It might be asked why a standard approach such as PRINCE2 has not been adopted. In fact there is an
outline of the PRINCE2 framework in an Appendix to the textbook. There has been caution about using
PRINCE2 more centrally because:
•
PRINCE2 tend to be used mainly in the UK and many users of the Software Project
Management textbook are from elsewhere
•
The content of this course would be vulnerable to changes to the method imposed by its
design authority
•
PRINCE2 tends to focus more on procedural and bureaucratic matters at the expense of
techniques – the few planning techniques that are associated with PRINCE, for example, the
development of product flow diagrams, are used in the Step Wise approach as well.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 38

---
This is an overview of the main steps:
0. Select project There must be some process by which the project to be executed was
selected. Chapter 3 on project evaluation looks at this in more detail.
1. Identify project objectives It is important that at the outset the main stakeholders are all
aware of the precise objectives of the project. This has already been discussed in Chapter 1.
2. Identify project infrastructure This may not be a significant step where you are working on
an in-house project in a very familiar environment. However, where the project is being
carried out for external clients then you may need to investigate the characteristics of the
environment in which the project is to be carried out.
3. Analyse project characteristics Different types of project will need different technical and
management approaches. For example, a project to implement control software embedded
in industrial equipment will need a different set of methods than a project to implement a
business information system. A multimedia application would again need a different set of
activities. (This is not to say that there could not be considerable overlaps in the approaches).
4. Identify products and activities With software projects, it is best to start by listing the
products, both deliverable and intermediate, to be created. The activities needed to create
the products can then be identified
5. Estimate effort for activity.
6. Identify activity risks Having assessed the amount of effort and the elapsed time for a
project, the reasons why these might be vary during the actual execution of the project need
to be considered. Where there is a very high risk of additional effort/time being needed then
actions to reduce this risk may be formulated.
7. Allocate resources With software projects, these resources will mainly be staff, but could
be equipment etc.
8. Review/publicize It is no good having a plan if no one knows about it
9. Execute Plan
10. Lower level planning Not all of a project, especially when it is large, can be planned in
detail at the outset. Not all the information needed to plan the later stages will be available
at the beginning: for example software development cannot be broken down into precise
sub-tasks with realistic target times until more is known about what the overall design of the
system is known.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 39

---
A project scenario: Brightmouth College Payroll
College currently has payroll processing carried out by a services company
This is very expensive and does not allow detailed analysis of personnel data to be
carried out
Decision made to bring payroll ‘in-house’ by acquiring an ‘off-the-shelf’ application
The use of the off-the-shelf system will require a new, internal, payroll office to be set
up
There will be a need to develop some software ‘add-ons’: one will take payroll data and
combine it with time-table data to calculate the staff costs for each course run in the
college
The project manager is Brigette.
The last requirement – to build an ‘add-on’ – allows some software development issues to be
addressed!
Step 1 establish project scope and objectives
1.1 Identify objectives and measures of effectiveness
‘how do we know if we have succeeded?’
1.2 Establish a project authority
‘who is the boss?’
1.3 Identify all stakeholders in the project and their interests
‘who will be affected/involved in the project?’
1.1. Identifying objectives and measures of effectiveness. This was discussed in chapter1. Key

points are that the student project objectives must be such that a student can realistically be
responsible for their achievement. For instance, an objective to reduce conflict between
project team members would be at too high a level for a software developer: he or she is there
to produce software and evaluation of the particular pyschometric test would be outside their
capabilities. If the student was a psychology student and the project was regarded as a
psychological one, then things might be different.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 40

---
1.2.Establishment of a project authority In the case of students on placement or carrying final

year projects for outside organizations, the problem of identifying who has the final say on
the project can occur surprisingly often, particular when different user groups have conflicting
requirements. In larger, more formal projects, the project authority might reside in a Project
Board or steering committee.
1.3 Identify all stakeholders in the project and their interests. Stakeholders can be anyone

who has an interest in the project. They may be users of the final application or might be
involved in the development or implementation of the project.
1.4 Modify objectives in the light of stakeholder analysis
‘do we need to do things to win over stakeholders?’
1.5 Establish methods of communication with all parties
‘how do we keep in contact?’
1.4 Modify objectives in the light of stakeholder analysis. The key point here is the need to

ensure commitment to the project from the important stakeholders. This might need to be
done by ensuring that there is some benefit from the project for them. Note this is a similar
idea to Barry Boehm’s ‘Theory W’ (‘W’ stands for ‘everyone a winner’)
1.5 Establish methods of communication with all parties In the case of a small student

project, it might be mainly swapping email addresses and mobile phone numbers. With larger
projects, it could involve setting up groups who meet regularly to co-ordinate action.
Sometimes specific ‘communication plans’ are drawn up to deal with these issues.
Back to the scenario
Project authority
-
Brigette finds she has two different clients for the new system: the finance
department and the personnel office. A vice principal agrees to be official client,
and monthly meetings are chaired by the VP and attended by Brigette and the
heads of finance and personnel
-
These meetings would also help overcome communication barriers
Applying these ideas to the scenario introduced earlier:
•
Project authority
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 41

---
•
Stakeholders/revision to objectives The application will not ultimately be a success if
project team members are not happy to use the system. They might be happier to use
the testing system if the results of their own tests were automatically notified to them
personally by the software application, so that this might have to be added as a
requirement for the project.
Stakeholders
For example, personnel office would supply details of new staff, leavers and
changes (e.g. promotions)
To motivate co-operation Brigette might ensure new payroll system produces
reports that are useful to personnel staff
Step 2 Establish project infrastructure
2.1 Establish link between project and any strategic plan
‘why did they want the project?’
2.2 Identify installation standards and procedures
‘what standards do we have to follow?’
2.3. Identify project team organization
‘where do I fit in?’
At the same time as establishing exactly what the project objectives are, the person

responsible may know little about the organizational environment in which the application is
to be developed and implemented. The actions in Step 2 address this problem.
Step 3 Analysis of project characteristics
3.1 Distinguish the project as either objective or product-based.
Is there more than one way of achieving success?
3.2 Analyse other project characteristics (including quality based ones)
what is different about this project?
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 42

---
Step 3 is about examining the nature of the application to be built and the environment in

which it is to be built and implemented and identifying the most appropriate technical
approach.
3.1 Objective-based versus product-based projects. With a product-based project the

developers have to create a product, the specification of which is often (but not always) clearly
defined. In an objective-based project, a problem is defined that needs to be solved but there
could be more than one solution. For example, if an organization needed a payroll application
they might consider (a) writing the system themselves (b) using a service company to do the
payroll for them (c) acquire an off-the-shelf package
3.2 Analyse other project characteristics – such as is it an information system or an

embedded real time or a multimedia application? Is it safety-critical? Etc etc. The payroll
application is clearly an information system. If an off-the-shelf application is adopted, there is
plenty of guidance on how off-the-shelf applications can be accessed and selected that could
be consulted by Brigette
Identify high level project risks
‘what could go wrong?’
‘what can we do to stop it?’
Take into account user requirements concerning implementation
Select general life cycle approach
waterfall? Increments? Prototypes?
Review overall resource estimates
‘does all this increase the cost?’
Identifying high level risks could influence the general approach to the project. For example, if

the users appeared to be uncertain about the precise nature of the requirement then a more
iterative approach, including the use of prototypes to refine user needs, might be selected.
If the application is very large and complex then breaking it down into increments might be

the way to proceed. Chapter/lecture 4 looks at this in more detail.
Back to the scenario
Objectives vs. products
An objective-based approach has been adopted
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 43

---
Some risks
There may not be an off-the-shelf package that caters for the way payroll is
processed at Brightmouth College
Answer?
Brigette decides to obtain details of how main candidate packages work as soon
as possible; also agreement that if necessary processes will be changed to fit in
with new system.
Step 4 Identify project products and activities
4.1 Identify and describe project products - ‘what do we have to produce?’
Here we follow the PRINCE approach of firstly identifying the products to be created. These products
could be deliverables that will eventually be handed over to the customer, or intermediate products
such as specifications and design documents, that are produced along the way.
The PBS is a way of listing these products.
In the scenario, one set of products will relate to the products needed to produce one or more
invitations to tender (ITTs) to supply the hardware and software needed to operate the new payroll
application. In order to allow the most suitable configuration to be identified the number of
transactions and the size of the database needed will have to be identified – volume figures. To set up
an appropriate network attached to secure printers and servers, a layout of the proposed office will
need to be created. A user requirement will need to be produced which describes the existing system,
identifies additional requirements (such as the need to be able to access database details in order to
produce one-off queries and reports), and some test data and expected results which further
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 44

---
illuminate the details of the requirements. This test data could form the basis of user acceptance tests.
A list of potential suppliers to whom ITTs could be sent will be needed, and the actual ITT itself which
will, among other things, explain how the proposals of potential suppliers are to be submitted.
Products
The result of an activity
Could be (among other things)
 physical thing (‘installed pc’),
a document (‘logical data structure’)
a person (‘trained user’)
a new version of an old product (‘updated software’)
The following are NOT normally products:
activities (e.g. ‘training’)
events (e.g. ‘interviews completed’)
resources and actors (e.g. ‘software developer’) - may be exceptions to this
Products CAN BE deliverable or intermediate
Product description (PD)
Product identity
Description - what is it?
Derivation - what is it based on?
Composition - what does it contain?
Format
Relevant standards
Quality criteria
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 45

---
Create a PD for ‘test data’
The names of products on the PBS can be rather vague. If you were to ask someone to produce, for
example, the ‘analysis report’ in the usability testing scenario, then you would need to explain exactly
what you mean by that. This is done via a Product Description. PDs can usually be re-used from one
project to another.
Note that they are different from specifications – the explain in general terms what a product is and
the description is relevant to all instances of that product. A specification describes a particular
instance within the class of products.
4.2 document generic product flows
The product flow diagram shows the order in which the products have to be completed. Effectively it
defines a method of working. The example above is a possible solution to Exercise 3.3 in the textbook.
The flow of the PFD is generally from top to bottom and left to right. We do no put in lines which loop
back. This is not because iterative and back-tracking is not accepted. Rather it is that you can in theory
jump back to any preceding product.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 46

---
Step 4.3 Recognize product instances
The PBS and PFD will probably have identified generic products e.g. ‘software modules’
It might be possible to identify specific instances e.g. ‘module A’, ‘module B’ …
But in many cases this will have to be left to later, more detailed, planning
Step 4.4. Produce ideal activity network
Identify the activities needed to create each product in the PFD
More than one activity might be needed to create a single product
Hint: Identify activities by verb + noun but avoid ‘produce…’ (too vague)
Draw up activity network
An ‘ideal’ activity
The activity network is the basis of the data that is input to planning software tools like MS Project.
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 47

---
Step 4.5 Add check-points if needed
There are some points in the project when we want to check that the quality of what we have done so
far is a sound basis for further work. In the example we have decided to check that all the module
designs are compatible with one another before continuing. Note that the benefit of reducing wasted
work at a later stage when incompatibilities lead to products being reworked, has to be balanced
against the delay caused by the check-point. The start of coding of modules A, B and C all have to wait
for the completion of the design of all the modules A, B and C. With no check-point, module A could
be coded as soon as the design of module A had been done without having to wait for B and C.
Step 5:Estimate effort for each activity
5.1 Carry out bottom-up estimates
distinguish carefully between effort and elapsed time
5.2. Revise plan to create controllable activities
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 48

---
break up very long activities into a series of smaller ones
bundle up very short activities (create check lists?)
Effort is the total number of staff-hours (or days etc) needed to complete a task.

Elapsed time is the calendar time between the time task starts and when it ends. If 2
people work on the same task for 5 days without any interruption, then the effort is 10
staff-days and the elapsed time is 5 days.
Using the PBS/PFD to generate the activities often means that some activities are very

small and others are huge. Often there is an activity called ‘write software’ which is
70% of a software development project. These large activities need to be broken down
into more manageable small tasks. You should aim for the average length of your
activities to be about the time between progress meetings e.g. if you have team
progress meeting once a fortnight, try to make the tasks last about 2 weeks.
Step 6: Identify activity risks
6.1.Identify and quantify risks for activities
damage if risk occurs (measure in time lost or money)
likelihood if risk occurring
6.2. Plan risk reduction and contingency measures
risk reduction: activity to stop risk occurring
contingency: action if risk does occur
Note that we have already considered some high level risks that could affect the project as a whole at
Step 3. Estimates of the effort and duration of activities can be quite tricky. When you produce an
estimate for an activity it is worth reflecting about the events which could cause the assumptions upon
which you have based your estimate to be wrong. Where the risk seems very high, then you might try
to introduce new activities specifically designed to reduce the risk, or to formulate a contingency
action if the risk should materialize. For example, there is not much you can do to stop people getting
the flu at a critical time in the project, but you might be able to have a plan to bring in temporary
cover for sickness in the case of time-critical activities.
6.3 Adjust overall plans and estimates to take account of risks
e.g. add new activities which reduce risks associated with other activities e.g.
training, pilot trials, information gathering
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 49

---
Step 7: Allocate resources
7.1 Identify and allocate resources to activities
7.2 Revise plans and estimates to take into account resource constraints
e.g. staff not being available until a later date
non-project activities
You now need to allocate resources (in particular, staff) to the activities in the plan. Where there is a
resource constraint, that is there are not enough staff (or other resource) of the right type to start all
the activities that run in parallel at the planned time, then the start of some activities may need to be
delayed until the appropriate resources are available.
We now have the basic information needed to produce a plan. One way of presenting the plan is by
means of a Gantt chart (named after Henry Gantt).
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 50

---
Step 8: Review/publicise plan
8.1 Review quality aspects of project plan
8.2 Document plan and obtain agreement
Step 9 and 10: Execute plan and create lower level plans
We have noted already that it is not feasible to produce a detailed plan for all stages of the project
right at the beginning of the project planning process and not all the information needed for the
detailed planning of the later stages is available at the outset. Initially an outline plan for the whole
project would be produced, plus a detailed plan for the first stage.
Key points
Establish your objectives
Think about the characteristics of the project
Discover/set up the infrastructure to support the project (including standards)
Identify products to be created and the activities that will create them
Allocate resources
Set up quality processes
Video lectures - https://www.youtube.com/c/TirupParmar & Notes :- https://t.me/bscit
Page 51